## Folha1
Time Line
Stage | Date |  |  |  | Notes
| Start |  | End
| Expected | Started | Expected | Ended
Part 1: Login Fully working with Google and Facebook as Auth methods | 2026-01-06 | 2026-01-06 | 2026-01-16 | 2026-01-21 | Fully working with Google
Part 2: Project fully complete and working | 2026-01-06 | 2026-01-06 | 2026-02-18
Beguinning of project | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06
Architectural Planning and Planning the Tech Stack | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-07 | Had to be changed later (22-1-2026)
Auth_Services | 2026-01-07 | 2026-01-07 | 2026-01-14 | 2026-01-21 | Login with google and password changes/recovery toke way longer then expected.
Database 1st Draft | 2026-01-06 | 2026-01-06 | 2026-01-08 | 2026-01-08
Database Final Version | 2026-01-08 | 2026-01-22 | 2026-01-21
RestAPI | 2026-01-14 | 2026-01-22 | 2026-01-28 |  | Delay on start caused by login taking too long.
Users (base) |  |  |  |  | 70% - falta separar entre Formadores e Alunos
Cursos |  |  |  |  | 40% falta adicionar, adicionar modulos e editar
Modulos |  |  |  |  | 70% falta editar
Turmas |  |  |  |  | 0%
Salas |  |  |  |  | 0%
Horarios |  |  |  |  | 0%
Disponibilidade |  |  |  |  | 0%
Relação Formadores turma modulo |  |  |  |  | 0%
Creiação de Horarios automáticos |  |  |  |  | 0%
WebSite | 2026-01-14 |  | 2026-02-04
Login 2FA |  |  |  |  | 100%
Login Google |  |  |  |  | 100%
Reset pass |  |  |  |  | 100%
change Password |  |  |  |  | 100%
Pagina home para alunos |  |  |  |  | 0%
Pagina home para Formadores |  |  |  |  | 0%
Pagina para gerir users geral |  |  |  |  | 80% Precisa de polimento, mas está funcional
Pagina para gerir Alunos |  |  |  |  | 0%
Página para gerir Formadores |  |  |  |  | 0%
Marcação de diponibilidade para formadores |  |  |  |  | 0%
Marcção de disponibilidade para salas |  |  |  |  | 0%
Chat Bot |  |  |  |  | 0%
Mobile APP (android) | 2026-02-02 |  | 2026-02-16 |  | 0%
Relatório final | 2026-02-12 |  | 2026-02-18 |  | 0%